## MedKey 2019-2020
Planification du projet MedKeyHabitats II 2019-2020
| Description des activités | 2019 | [11 empty] | 2020
|  | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
Strategy 1 | Improve knowledge on species and habitats affected by unsustainable fishing practices
Result 1.1 | Hotspots, migratory, patterns, forging grounds, habitats distribution and Ecosystems value/services are known
Activity 1.1.1 | Mapping selected key habitats using conventional methods (transects, aerial photos) and / or innovative (satellite imagery and side scan sonar) and Set up and enhancing monitoring systems for marine key habitats
Element 1.1.1.1 | Morocco | bar: 2019 J to 2020 S
Phase 3 (élaboration des cartes) | bar: 2019 O to 2019 N
Organisation d'un atelier national pour la présentation des résultats | bar: 2019 D
Element 1.1.1.2 | Tunisia | bar: 2019 J to 2020 S
phase 2 (travail terrain) | bar: 2019 J to 2019 O
Phase 3 (élaboration des cartes) | bar: 2019 N to 2019 D
Organisation d'un atelier national pour la présentation des résultats | bar: 2020 J
Element 1.1.1.3 | Turkey | bar: 2019 J to 2020 S
Phase 1 (phase de diagnostic) | bar: 2019 J to 2019 A
Validation de la phase 1 (phase de diagnostic) | bar: 2019 S
phase 2 (travail terrain ) | bar: 2019 O to 2019 D
Phase 3 (élaboration des cartes) | bar: 2020 J to 2020 F
Organisation d'un atelier national pour la présentation des résultats | bar: 2020 M
Element 1.1.1.4 | Cyprus | bar: 2019 J to 2020 S
Etablissement d'une spatial data infrastucture (SDI) basée sur le plateforme de la biodiversité | bar: 2019 O to 2020 J
inventoraires des couches GIS à publier en ligne via le nœud national (SDI). | bar: 2019 S to 2020 J
Elaboration d'un plan national pour la conservation de la végétation marine | bar: 2019 S to 2020 J
atelier de clôture national pour la présentation des résultats | bar: 2020 M
Element 1.1.1.5 | Algeria | bar: 2019 J to 2020 S
Phase 3 (élaboration des cartes) | bar: 2019 O to 2019 N
Organisation d'un atelier national pour la présentation des résultats | bar: 2019 D
Element 1.1.1.6 | Malta | bar: 2019 J to 2020 S
Phase 1 (phase de diagnostic) | bar: 2019 S to 2019 O
réunion de validation de la pahse 1 | bar: 2019 O
phase 2 (cartographie ) | bar: 2019 O to 2020 J
Réunion de validation de la phase 2 | bar: 2020 F
Phase 3 (élaboration des cartes) | bar: 2020 F to 2020 M
Organisation d'un atelier national pour la présentation des résultats | bar: 2020 A
Activity 1.1.2 | Improvement of the scientific knowledge on marine key habitats
Element 1.1.2.1 | Improvement of the scientific knowledge on marine key habitats - Platfome update | bar: 2019 O to 2020 M
Element 1.1.2.1 | Rapport sur les biocenoses des grottes en Mediterranée | bar: 2019 M to 2019 J
Element 1.1.2.2 | Closure workshop - Project MedKeyHabitats | bar: 2020 J
Result 1.2 | Impact of fishing on Selected Habitats is evaluated Relevant data for adressing unsustainable fishing is available and sensitive areas are identified and integrated into marine spatial plans
Activity 1.2.1 | Socio-economic evaluation of the impact of fishing on habitats | bar: 2019 J to 2020 S
Element 1.2.1.1 | Morocco | bar: 2019 J to 2019 N
Element 1.2.1.2 | Tunisia | bar: 2019 J to 2019 N
Element 1.2.1.3 | Turkey | bar: 2019 O to 2020 M
Element 1.2.1.4 | Cyprus | bar: 2019 J to 2020 S
etude socio-economique et l'évaluation de la vulnérabilité des herbiers de Posidonie aux activités de pêche dans la future AMP Cape Greko . | bar: 2019 O to 2020 M
etude pilote sur l'impact socio-économique des espèces invasives | bar: 2019 O to 2020 M
mise en place un point de surveillance de l’étendue des herbiers de Posidonie. | bar: 2019 O to 2020 M
Element 1.2.1.5 | Algeria | bar: 2019 J to 2019 N
Element 1.2.1.6 | Malta | bar: 2019 O to 2020 M
Strategy 2 | Capacity building of relevant actors for implementing sustainable fishing practices
Result 2.1 | Relevant actors have skills and means to implement monitoring, control and surveillance
Activity 2.1.1 | organisation of Symposia on marine key habitats
Element 2.1.1.1 | organisation of Symposia on marine key habitats | bar: 2019 J; 2020 O to 2020 N
Activity 2.1.2 | Regional training on the using of GIS in the mapping of marine key habitats, and in the elaboration of sensitivity maps of habitats to fishing activities
Element 2.1.2.1 | Regional training on the using of GIS in the mapping of marine key habitats, and in the elaboration of sensitivity maps of habitats to fishing activities | bar: 2019 D to 2020 J; 2020 O to 2020 D
Activity 2.1.3 | on job training on the mapping of marine key habitats, Setting up of monitoring systems
Element 2.1.3.1 | On job training on the mapping of marine key habitats, Setting up of monitoring systems | bar: 2019 M to 2019 D
Strategy 3 | Awareness raising of fishermen and other target groups
Result 3.1 | NGOs, fishermen org and all relevant stakeholders advocate for sustainable fishing activities
Activity 3.1.1 | Awarness of fishermen about the importance of the marine key habitat in relation with the fishing resources and role of marine protected areas in preserving sustainable fishing resources
Element 3.1.1.1 | Elaboration de posters, actions de communication ponctuelles tout au long de la durée du projet | bar: 2019 J to 2020 J
Element 3.1.1.2 | short movies produced on the importance of marine key habitats and the MPAs | bar: 2019 O to 2020 J
Element 3.1.1.3 | Viste of fishermen to MPAs with sustainable fishing practices | bar: 2019 D